The First Annual Student Megaconference

May 6th 2004

# Overview

The Student Megaconference (Megaconference Jr.) is a new project designed to give students in elementary and secondary schools around the world the opportunity to communicate, collaborate and contribute to each other’s learning in real time, using advanced multi-point video conferencing technology. Presenters will design and conduct videoconference-based presentations and activities focused on both academic and cultural issues.  Participants will be able to address questions to presenters and to collaborate with geographically diverse peers in collaborative learning activities, thus building international cultural awareness.

The program will meet many national and local curriculum standards in multiple subject areas. It will also help students and teachers develop the capacity to effectively utilize high-speed networks, videoconferencing and other emerging technologies to enhance learning outcomes.

## Who Can Participate

Presenters, activity leaders and audience members in Megaconference Jr. will be made up of students, teachers and technical staff from elementary, middle and secondary schools in the US and around the globe. University teacher education faculty and students are also welcome to participate. Participants will need to have access to the Internet2 Abilene Network in the US (or equivalent high-speed networks in countries outside the US that link to Abilene) at their schools or at a local university where they can participate. They will also need appropriate IP based (H.323) video conferencing capabilities and equipment.

We expect between 20 and 50 schools from at least 5 countries to participate interactively in the event, with others viewing one way streamed video. The event will run from 7 am until 7 pm (EST). The 12 hour duration will make it possible for schools from many time zones to participate during their regular school hours.

Internet2 University members, GigaPoPs, SEGPs, international MoU partners and appropriate governmental and educational agencies will be involved in providing high speed connectivity, videoconferencing facilities, technical support and other services to the K-12 participants.

Help Make it Happen

Elementary and secondary (K-12) teachers and students from around the world are needed NOW to work on the three planning committees listed on the next page. Participation in a committee will provide the opportunity to engage in weekly communications with international team members towards organizing and completing committee goals. (We request that no more than one teacher and one student from any school be involved in the planning.) To participate contact:

Jennifer MacDougall

MAGPI GigaPoP

jmacdoug@magpi.net

+1-215-898-0341 (phone)

Megaconference Jr. 2004 Planning Committees and their Responsibilities:

Technical Committee

- Create, maintain and update event website and investigate multi-lingual capabilities

- Manage Web based registration database and create appropriate forms as necessary

- Determine Web hosting requirements and location

- Develop and disseminate technical (network) participation requirements

- Determine possible # of participating sites per timeframe and types of connections

- Assemble and distribute technical troubleshooting guidelines

- Coordinate video streaming and archiving of the event

- Coordinate network testing and troubleshooting

- Coordinate chat room(s) for technical support

# Program Committee

- Define event format and structure

- Solicit, schedule and oversee event presentations and activities

- Oversee the nature and form of event content

- Create request for presentation proposals

- Manage program/content related issues and questions

- Communicate with presenters and activity leaders

### Operations and Outreach Committee

- Develop planning and event timetable and schedule

- Create event promotional materials

- Manage event outreach and insure adequate knowledge of event and participation

- Create event logo, Web site and document design

- Manage registration and communications with participants

- Define and manage event parameters, ie, maximum number of participants, etiquette protocols, etc.

- Manage administrative affairs and issues

Student Megaconference Planning Timeline:

- Planning Committees operating: by February 15, 2004

- Event Registration Open: March 1, 2004

- Presentation and Activity Proposals due by: March 15th 2004

- Registration Deadline April 15th (for guaranteed participation)

- Megaconference Jr. Event: May 6, 2004

Want to know what Megaconference V was like?  You can view the highlights clip at: www.pelegroup.net/resources/megaconferenceV/megaconfV-2.mov