## 3.0
perfSONAR 3.0 - Expected Release date : 31 March 2008
| Product | Feature | Priority | Raised by | Implementer | Verification | Resources
1 | RRD MA | Capability to retrieve data from RRD files
2 | SQL MA | Capability to retrieve and store data from SQL database
3 | SSH-Telnet MP | Capability to execute commands on routers
|  | XML based metadata configuration file | High | Loukik | Stijn
Enhanced list of commands
4 | XML LS
5 | AS
6 | BWCTL MP
7 | Web Admin | Capability to administer software via web pages | High | Loukik | Michalis
|  | Servlets for property files (service.prop components.prop, log.prop) |  | Loukik | Michalis
|  | Wizard servlets for quick configuration of a service |  | Loukik | Each developer
|  | Servlets for exist database |  | Loukik | Michalis
|  | Servlets for sql ma administration |  | Loukik | Michalis
8 | perfSONAR Base
|  | Base versioning | Medium | Loukik
|  | Log configuration file same across all services | Medium | Gina | Michalis
|  | Grouping of properties in configuration file | Medium | Gina | Each developer
|  | Authentication using eduGAIN + GiDP | High | Nicolas | Candido, Developers
9 | Common features
|  | RPMs for all services (for RHEL 5 and Fedora) | High | Loukik | Guilherme
|  | RPMs for tomcat, exist | High | Loukik | Guilherme
|  | WAR files for all services released | High | Loukik | Roman
|  | Change logs for all services in specified directory | Medium | Loukik | Szymon
|  | Debian packages for all services | Medium | Nicolas | Guilherme
|  | No version nos in Access point URLs | High | Loukik, Chris | Guilherme
Other improvements for this release cycle
|  | Feature | Priority | Raised by | Implementer | Verified by | Ready for
1 | Procedural
|  | Release specification | High | LK, ST, Developers | ST, LK, LM | ST, LK, LM
|  | Product build guide | High | Loukik | LK, GF, MM | LK
|  | Documented test cases for all services | High | Loukik | Michalis, Testers

## 3.1
perfSONAR 3.1 - Expected Release date : June 1st week 2008
|  | Feature | Priority | Raised by | Implementer | Co-ordination | Sign off | Other Resources | Comments
1 | RRD MA | Capability to retrieve data from RRD files
|  | Performance benchmarking scripts | High | Loukik | Ilias/Panagiotis | Michalis | MM, RL, LK
|  | New metric - Packet count at interface | Low | Nicolas | Roman | Nicolas | Nicolas |  | move to 4.0
|  | Domain field per interface | Medium | Loukik | Roman | Loukik | Loukik | LK, ST, MM
2 | SQL MA | Capability to retrieve and store data from SQL database
|  | e2emon Sync compatibility | High | Loukik | Roman | Loukik | Loukik | MM, MK, LK
|  | New metric - Packet count at interface | Low | [5 empty] | move to 4.0
|  | Domain field per interface | Medium | [5 empty] | move to 4.0
3 | SSH-Telnet MP | Capability to execute commands on routers
|  | Fix design flaw (command conversion between manufacturer types) | Medium | Nicolas | Stijn | Nicolas | Nicolas
4 | XML LS
|  | Distributed Lookup Service (prototype) ? | Low | Nicolas | Maciej |  |  |  | move to 4.0
|  | Global LS | High | Nicolas | Maciej | Nicolas | Nicolas | Szymon
5 | AS
|  | Automation of AS testing (SAML assertions) | Medium | Michalis | David | Michalis | Michalis | Candido | Priliminary investigation
6 | BWCTL MP
|  | Test scripts on SOAP UI | Low | Michalis |  |  |  |  | move to 4.0
7 | Web Admin | Capability to administer software via web pages
|  | Stitching capability , general enhancements to web admin | Medium | Loukik | Michalis | Michalis, Loukik | Loukik, Gina | Gina
|  | Restore to factory settings option ? | Low | Loukik |  |  |  |  | move to 4.0
|  | Deployment testing servlet - investigation | Medium | Loukik, Michalis | Prodromos | Michalis, Loukik | Loukik, Gina | Verena
8 | perfSONAR Base
|  | XML based configuration files | low | Loukik, Dev group |  |  |  |  | move to 4.0
|  | Time of execution for each request logged (performance log) | medium | Loukik, Dev group | Roman, Maciej | Loukik | Loukik, SD | Loukik, Szymon | effort evaluation required
9 | pS UI
|  | New metric - Packet count at interface stored in RRD | Low | Nicolas | Roman |  |  |  | move to 4.0
|  | Looking glass integration | High | Nicolas | Stijn | Nicolas | Nicolas, SD | Stijn
|  | Interface domain information for RRD MA and SQL MA | Medium | Loukik | Nina | Loukik | Loukik, SD | ST
|  | Global LS integration | High | Nicolas | Nina | ST | NS
10 | DFN CNM
|  | New metric - Packet count at interface stored in RRD | Low | Nicolas | Roman |  | Nicolas |  | move to 4.0
11 | HADES websystem
12 | Common features
|  | 2 Tier monitoring of services (service + resource) - specification | High | Service Desk, Nicolas | Luchesar | Nicolas | Nicolas, SD | Verena, Jochen | High Risk
|  | 2 Tier monitoring of services - development | High | Service Desk, Nicolas | Luchesar, Roman | Nicolas, ST | Nicolas, Szymon | Verena, Jochen | High Risk
|  | 2 Tier monitoring of services - integration | High | Service Desk, Nicolas | Luchesar | Nicolas, ST | Nicolas | Verena, Jochen | High Risk
|  | Software update and config backup | Low | Loukik | Guilherme, Gijs, Loukik |  | Loukik
Server Benchmarking
|  | Virtual machine flavor? | low | ? |  |  |  |  | move to 4.0
|  | Dynamic configuration update ? | low | Loukik, Michalis |  |  |  | Prodromos, RL, MG
Other improvements for this release cycle
|  | Feature | Priority | Raised by | Implementer |  | Sign off | Other resources
1 | Procedural
|  | Release tasks planning | High | LK, LM, MM | LK, LM | LK | LK, NS
|  | Product roadmap | High | LK | LK | LK | WILs
|  | Build process setup and execution | High | LK, LM | LK, GM, GF | LK | LK
|  | Web Admin integration process - proper definition | Medium | LK, MM
Other
perfSONAR MDM webpages
perfsonar.eu webpages
Protocol documentation and standardization

## 3.1v2
perfSONAR 3.1 - Expected Release date : June 1st week 2008
|  | Feature | Priority | Raised by | Implementer | Co-ordination | Sign off | Other Resources | Comments
1 | RRD MA | Capability to retrieve data from RRD files
|  | Performance benchmarking scripts | High | Loukik | Ilias/Panagiotis | Michalis | MM, RL, LK
|  | Domain field per interface | Medium | Loukik | Roman | Loukik | Loukik | LK, ST, MM
2 | SQL MA | Capability to retrieve and store data from SQL database
|  | e2emon Sync compatibility | High | Loukik | Roman | Loukik | Loukik | MM, MK, LK
3 | SSH-Telnet MP | Capability to execute commands on routers
|  | Fix design flaw (command conversion between manufacturer types) | Medium | Nicolas | Stijn | Nicolas | Nicolas
4 | XML LS
|  | Global LS | High | Nicolas | Maciej | Nicolas | Nicolas | Szymon
5 | AS
|  | Automation of AS testing (SAML assertions) | Medium | Michalis | David | Michalis | Michalis | Candido | Priliminary investigation
6 | BWCTL MP
7 | Web Admin | Capability to administer software via web pages
|  | Stitching capability , general enhancements to web admin | Medium | Loukik | Michalis | Michalis, Loukik | Loukik, Gina | Gina
|  | Deployment testing servlet - investigation | Medium | Loukik, Michalis | Prodromos | Michalis, Loukik | Loukik, Gina | Verena
8 | perfSONAR Base
|  | Time of execution for each request logged (performance log) | medium | Loukik, Dev group | Roman, Maciej | Loukik | Loukik, SD | Loukik, Szymon
9 | pS UI
|  | Looking glass integration | High | Nicolas | Stijn | Nicolas | Nicolas, SD | Stijn
|  | Interface domain information for RRD MA and SQL MA | Medium | Loukik | Nina | Loukik | Loukik, SD | Szymon
|  | Global LS integration | High | Nicolas | Nina | Szymon | Nicolas
10 | DFN CNM
11 | HADES websystem
12 | Common features
|  | 2 Tier monitoring of services (service + resource) - specification | High | Service Desk, Nicolas | Luchesar | Nicolas | Nicolas, SD | Verena, Jochen | High Risk
|  | 2 Tier monitoring of services - development | High | Service Desk, Nicolas | Luchesar, Roman | Nicolas, Szymon | Nicolas, Szymon | Verena, Jochen | High Risk
|  | 2 Tier monitoring of services - integration | High | Service Desk, Nicolas | Luchesar | Nicolas, Szymon | Nicolas | Verena, Jochen | High Risk
|  | Software update and config backup | Low | Loukik | Guilherme, Gijs, Loukik |  | Loukik
Server Benchmarking
|  | Dynamic configuration update ? | low | Loukik, Michalis |  |  |  | Prodromos, RL, MG
Other improvements for this release cycle
|  | Feature | Priority | Raised by | Implementer |  | Sign off | Other resources
1 | Procedural
|  | Release tasks planning | High | LK, LM, MM | LK, LM | LK | LK, NS
|  | Product roadmap | High | LK | LK | LK | WILs
|  | Build process setup and execution | High | LK, LM | LK, GM, GF | LK | LK
|  | Web Admin integration process - proper definition | Medium | LK, MM
Other
perfSONAR MDM webpages
perfsonar.eu webpages
Protocol documentation and standardization

## 4.0
perfSONAR 4.0 - Expected Release date :
|  | Feature | Priority | Raised by | Implementer | Verification | Completed on
1 | RRD MA | Capability to retrieve data from RRD files
2 | SQL MA | Capability to retrieve and store data from SQL database
3 | SSH-Telnet MP | Capability to execute commands on routers
4 | XML LS
5 | AS
6 | BWCTL MP
7 | Web Admin | Capability to administer software via web pages
8 | perfSONAR Base
|  | Dynamic configuration update | medium | Loukik, Michalis
9 | Common features
|  | 3 Tier monitoring of services | High | Service Desk | Luchesar | Nicolas
Other improvements for this release cycle
|  | Feature | Priority | Raised by | Implementer | Verified by | Ready for
1 | Procedural
|  | Release tasks planning | High | LK, LM, MM | LK, LM
|  | Product roadmap | High | LK | LK

## Bucket
Features that have been listed but not approved and assigned for any particular release are available below
Product flavors | Virtual machine flavor | Requester | Status
Web Service product features
* SSH/telnet MP – remove telnet, thorough command testing on testbed
| Move away from axis v1 to axis v2 (for performance reasons) - | Maciej
| Move to Java 1.6 (Maciej) | Maciej
New service: Transformation service for resolution (client need 30 min resolution and the service is of 1min)
New service: Resource protection - JR
Feature: local Resource protection on a web-service
Feature: LS registration protocol extension (keepalives-deregistration)
Perfsonar base jar and nm-wg jar to possibly be re-written (no maintenance)
| Log using sys log (minor modifications to log4j) | Service desk
performances improvements
RRD MA - GPS co-ordinates in metadata
| Jetty based flavor | Chris, SD
Messages
* Limiting requests based on work load
* Messages to gather system information
AA | * Issuer based check and validity check of certificates
IP addresses based access at program level – investigation
Authorisation
Visualisation tools | * Limit CNM’s regular fetching capabilities?
Documentation, Schemas | Balance between flexibility of the schema and define entities (string is not helpful, proper specification is required : semantics) | developers
Timestamps and data types (schema quite flexible and they are defined outside the schema – proper specification of the features that should be implemented)
Schema evolution: nmtime specification
Schema evolution: URL as result code
Schema evolution : Support for SA6 measurements (schema definition)
Schema evolution: Error codes not documented
Cleaning the code (standardise the error codes, information to be registered to the LS has to be made more consistent)
Documentation enhancements : schema not complete – semantics (rnc files to be complete)
Processes | Software design and development process