## Sheet1
| 2008-08-29 | 2008-09-05 | 2008-09-12 | 2008-09-19 | 2008-09-26 | 2008-10-03 | 2008-10-10 | 2008-10-17 |  | 2008-11-10
AS | CR dev |  | DM funct test | Beta test |  | fixes | release |  | ? | LHC-OPN
hLS | MG dev |  | xx manual checks |  | Beta test | fixes | release |  | MDM | LHC-OPN
RRD MA | RL dev -> 3/9 |  | xx funct test | Beta test |  | fixes | release |  | MDM | LHC-OPN
SQL MA | RL dev | SC func test |  | Beta test |  | fixes | release |  |  | LHC-OPN
TTSSH | SM dev |  |  | PP funct test | Beta test | fixes | release |  | MDM | LHC-OPN
BWCTL MP | VV dev |  | SM test |  | Beta test | fixes | release |  |  | LHC-OPN
Flow Agg MA | 2008-09-12: SC test; 2008-09-19: Beta test; 2008-10-03: fixes; 2008-10-10: release
CL MP | 2008-09-26: Beta test
beta could start with AS, RRD, SQL, flow aggregation MA
tomcat | 2008-08-29: RL + SC; 2008-09-19: Test infrastructure would contain: the AS used for beta testing and the hLS from Maciej release (not yet functionally tested, but OK).
web-admin | 2008-09-12: LI - parameter check; 2008-09-26: Beta testing continue with the addition of the hLS, TTSSH and BWCTL MP
CNM | 2008-09-05: DS - CNM to retrieve data (*)
pSUI | 2008-09-05: NJ - pSUI to retireve data (*); 2008-09-19: Beta tester uses the tool to verify data retrieval
NS - list functionality changes for GUI developers
Repository | 2008-08-29: Vmware for repo; 2008-09-12: SC populate; 2008-09-19: SC populate; 2008-10-10: SC repo for release ready
Doc | 2008-09-05: SK - Beta test tester docs and guidelines
Doc | 2008-09-05: SK - Beta tester list
Doc | 2008-09-05: GK - Installation guide ready
Infrastructure | 2008-10-10: ST - gLS on PSNC
GK - Announce release on ML
GK - update web-site
NS- give a push to Pilot
(*) | 2008-08-29: Use the test infrastructure and track with RC you tested against.
Indicates a development task done by a developer. It leads to a RC close to a final product (and has the .deb, rpms, new web-admin). A deployment on the test-infrastructure is mandatory with this RC (for the visualisation)
Indicates functional testing (final check). The web-services are ready for limited beta testing within JRA. Some of their features can still be broken.
Beta testing phase
Documentation and release, test preparation tasks.